## Gantchart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | Baymax- Dipression Detection System |  |  |  |  | INSTUTUTE & DEPARTMENT NAME | [6 empty] | A.P Shah Institute of Technology
PROJECT GUIDE |  | Prof. Apeksha Mohite |  |  |  |  | DATE | [6 empty] | 2021-02-10
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION(Weeks) | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Research paper search | Rupesh, Nikhil, Rajesh | 2020-09-05 | 2020-10-05 | 3 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Research paper finalization | Rupesh, Nikhil, Rajesh | 2020-10-11 | 2020-11-21 | 3 | 100% | bar: WEEK 2 W
1.2 | Project Title | Rupesh, Nikhil, Rajesh | 2020-11-25 | 2020-12-06 | 3 | 100% | bar: WEEK 2 W to WEEK 3 W
1.3 | Abstract | Rajesh | 2020-12-14 | 2020-12-15 | 1 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Objectives | Rupesh, Nikhil, Rajesh | 2020-12-13 | 2020-12-13 | 1 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Literature Review | Rupesh | 2020-12-14 | 2020-12-14 | 1 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Problem Definition | Rajesh | 2020-12-15 | 2020-12-15 | 1 | 100% | bar: WEEK 3 F
1.7 | Scope | nikhil | 2020-12-16 | 12-16-2020 | 1 | 100% | bar: WEEK 3 F
1.8 | Technology stack | Rupesh, Rajesh | 2020-12-17 | 2020-12-17 | 1 | 80% | bar: WEEK 3 F
1.9 | Benefits for environment | nikhil | 2020-12-18 | 2020-12-18 | 1 | 100% | bar: WEEK 3 F
1.1 | Benefits for society | nikhil | 2020-12-19 | 2020-12-19 | 1 | 80% | bar: WEEK 3 F
1.11 | Applications | Rupesh | 2020-12-20 | 2020-12-20 | 1 | 100% | bar: WEEK 3 F
2 | Project Design
2.1 | Proposed System | Nikhil, Rajesh | 2021-01-21 | 2021-01-23 | 2 | 70% | bar: WEEK 4 M to WEEK 4 R
2.2 | Design(Flow Of Modules) | Rupesh, Rajesh, Nikhil | 2021-01-24 | 2021-01-26 | 2 | 70% | bar: WEEK 4 F to WEEK 5 F
2.3 | Activity Diagram | Nikhil, Rajesh | 2021-01-27 | 2021-01-28 | 2 | 50%
2.4 | Use Case Diagram | Rupesh, Nikhil, Rajesh | 2021-01-29 | 2021-01-31 | 2 | 50%
2.5 | Description Of Use Case | Rajesh | 2021-02-01 | 2021-02-03 | 2 | 30%
2.6 | Modules
2.6.1 | Module-1 | Rupesh, Rajesh, Nikhil | 2021-02-04 | 2021-02-06 | 2 | 75%
2.6.2 | Module-2 | Rajesh | 2021-02-07 | 2021-02-08 | 2 | 85%
2.6.3 | Module-3 | Rupesh | 2021-02-09 | 2021-02-11 | 2 | 85%
2.6.4 | Module-4 | Rupesh | 2021-02-11 | 2021-02-13 | 2 | 85%
2.7 | Preparation Of Report | Nkhil, Rajesh | 2021-02-14 | 2021-02-16 | 2 | 75%
3 | Project Implementation
3.1 | Module-1 | Rupesh, Rajesh, Nikhil | 2021-02-17 | 2021-02-17 | 0 | 10%
3.2 | Module-2 | Rajesh | 2021-02-18 | 2021-02-18 | 0 | 0%
3.3 | Module-3 | Rajesh, Rupesh | 2021-02-19 | 2021-02-19 | 0 | 0%
3.4 | Module-4 | Nikhil, Rajesh | 2021-02-20 | 2021-02-21 | 0 | 0%
4 | Testing
4.1 | Design of Test Cases | Rupesh, Nikhil, Rajesh | 2021-02-23 | 2021-02-24 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F; WEEK 2 T to WEEK 2 F; WEEK 3 T to WEEK 3 F
4.2 | Architecture | Rupesh | 2021-03-10 | 2021-03-11 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.3 | Prototyping | Nikhil, Rajesh | 2021-03-12 | 2021-03-13 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.4 | Development | Rajesh | 2021-03-14 | 2021-03-15 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.5 | Testing QA | Nikhil, Rajesh | 2021-03-16 | 2021-03-17 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.6 | Bulding Up a virtual database | Rajesh, Rupesh | 2021-04-18 | 2021-04-18 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.7 | Configuration Of application | Nikhil | 2021-04-16 | 2021-04-17 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.8 | Worked on Fuzzy logic | Rupesh, Nikhil, Rajesh | 2021-04-18 | 2021-04-19 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.9 | Implementation of fuzzy logic and chat bot | Rupesh, nikhil, Rajesh | 2021-04-20 | 2021-04-20 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.1 | ipmplementation of motivvational thaughts | Nikhil, Rupesh | 2021-04-21 | 2021-04-21 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
4.11 | Configuration Of Expert | Rupesh | 2021-05-05 | 2021-05-11 | 1 | 0% | bar: WEEK 1 T to WEEK 1 F
5 | Results and Analyis
5.1 | Report Preparation | Nikhil, Rajesh | 2021-05-01 | 2021-01-06 | 1 | 70%
5.2 | Graphical Representation | Rupesh | 2021-05-06 | 2021-05-07 | 1 | 60%